## Лист1
Week | Task | Use | As Minimal Result | Problem
#1 | Describe the program's functionality in detail. Create interaction diagrams. | Define the database schema. Describe the REST API. Set up the repository and project structure. Implement a progress monitoring system. | Detailed program description. Interaction diagrams created. Initial database schema defined. REST API documented. Repository and project set up. Progress monitoring mechanism in place. | None
#2 | Create the Spring Boot project. Add necessary libraries. | Revise and optimize the application folder structure. Create core entities. Connect the project to the database. | Spring Boot project created. Required libraries added. Application folder structure optimized. Core entities defined. Project connected to the database. | None
#3 | Test functionality and database connection. Learn Spring Boot, Inversion of Control (IoC), and Dependency Injection (DI) principles. Decide on the necessity of Liquibase. Implement Repositories and DTOs. | Functional testing completed. Understanding of Spring Boot, IoC, and DI principles gained. Liquibase necessity determined. Repositories and DTOs implemented. | Should decide on the necessity of Liquibase. | Liquibase
#4 | Implement Service layer functionality. Implement Controller layer functionality. Verify project functionality. Implement different roles (admin, manager, employee). | Services layer implemented. Controllers functionalities added. Project functionality verified. Different roles (admin, manager, employee) defined. | None | Junit and Mochito with Spring
#5 | Write tests for the project. Create documentation. Decide on using Docker containers. | Comprehensive test suite created. Detailed documentation written. Docker container implementation determined. | Should decide on using Docker containers. | Docker